## Slide 1: IESP PMB meeting Planning of project activities – II project year
University of Montenegro
Ana Dragutinović
This project has been funded with support from the European Commission. This presentation reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein.

## Slide 2
WP2 - Capacity Building for Internationalization through staff training and equipment upgrade
2.2 | Development/redesign of English web sites of Montenegrin HEIs | – | Feb. 2021 | UoM, UNIM | For the UoM the selected service provider will continue and complete the development of web site. For the University Mediterranean the procurement of service provider will be finalised and then the new version of the web site developed.
2.3 | Know-how transfer to teaching staff related to the internationalization | – | Feb. 2021 | UoM, UDG, UNIM | A2.3.3 – Know-how transfer related to improving English skills of teaching staff for delivering courses in English. For the staff of UoM the remaining part of the English language training (course) has to be conducted, while for the staff of two other Montenegrin universities the trainings are supposed to start in January 2021.

## Slide 3
WP 3 - Development of Tools for Enhanced Internationalization
3.1 | Development of internationalization strategies and action plans | – | Feb. 2021 | UoM, UDG, UNIM, UL | Following the discussion at the PMB meeting on 13th of November 2020 and with additional assistance of the University of Ljubljana, each Montenegrin HEI will prepare a final version of its 5-year internationalization strategy with an action plan.
3.2 | Development of supporting documentation to internationalization | – | Feb. 2021 | UoM, UDG, UNIM | UoM wil prepare supporting documents related to projects, bilateral agreements and degree seeking students, and will finalise the draft version of supporting documents related to mobility. UDG and UNIM will finalise their supporting documentation.

## Slide 4
3.3 | Design of catalogues for courses offered in English | Feb. 2021 | March 2021 | UoM, UDG, UNIM | In order to support internationalization through incoming student mobility, each Montenegrin HEI will offer courses in English language at BSc/BA and MSc/MA levels starting from academic year 2021/22 (activity 4.3) and for that purpose will prepare course catalogues, which will contain a description of the course topics that will be covered, assignments and assessments students will be responsible for, as well as a list of learning outcomes. The preparation of catalogues will follow the completion of training for improving English skills of teaching staff for delivering courses in English (activity 2.3.3).

## Slide 5
3.4 | Development of pilot summer school in English with curricula | – | March 2021 | UoM | Summer school programs designed by UoM, including course content and the learning outcomes, application and recruitment procedures, arrangement of housing for the students and development of a social program. UoM will organise a meeting of project partners to present the programme and fine tune the curricula.
3.5 | Development of teaching materials in English | March 2021 | June 2021 | UoM, UDG, UNIM | Montenegrin HEIs teaching staff will develop teaching materials for each course in English at BSc/BA and MSc/MA levels and for summer school in English. Electronic versions of materials will be produced. All teaching materials will be approved by Montenegrin HEIs governing bodies.

## Slide 6
3.6 | Developing criteria for assessing quality of internationalization of Montenegrin HEIs | Feb. 2021- April 2021 | UoM, UDG, UNIM MoS, MoE, ACQAHE | Development of criteria for assessing quality of internationalization of Montenegrin HEIs - define indicators, tools and actors necessary for smooth and high quality implementation and montiring of internationalisation plans. Governmental partners will provide expert input on the contents of the criteria and their alignment with existing practices. Guidelines for quality assessment will be developed for each of the Montenegrin HEIs. A monitoring body will be established at each Montenegrin HEIs, which will be in charge of monitoring and quality assessment of the internationalization activities during project lifetime and at least during a 5-year period of implementation of internationalization strategy. It is foreseen that the University Mediterranean host a meeting during which Montenegrin HEIs will present guidelines and where fine tuning will be performed.

## Slide 7
WP 4 - Integration of Internationalization at Montenegrin HEIs
4.1 | Adoption and implementation of strategic documents | Dec. 2020 | Nov. 2021 | UoM, UDG, UNIM | Final versions of internationalization strategies and accompanying documents will be presented to the Montenegrin HEIs' governing bodies for adoption. Implementation of internationalization strategies, i.e. their action plans, as well as utilization of the supporting documents for internationalization will commence immediately after their adoption. Each Montenegrin HEI will organise information sessions with the staff from their units in order to successfully launch the new support system, and they will establish regular communication in order to have continuous feedback on the appropriateness of the adopted material. | 

## Slide 8
4.3 | Adoption and implementation of English courses offered at BSc and MSc levels | March 2021 | Nov. 2021 | UoM, UDG, UNIM | Catalogues of courses offered in English language at BSc/BA and MSc/MA levels will be presented to Montenegrin HEIs governing bodies for adoption. After adoption, if necessary, accreditation process will be conducted at National Agency for Quality Assurance of Higher Education. Realisation of courses will follow adoption (or accreditation) process and will start from academic year 2021/22.
4.4 | Adoption and implementation of pilot summer schools | March 2021 | July 2021 | UoM | Summer school curricula with course catalogues, in English, will be presented to UoM’s governing bodies for adoption. After adoption, accreditation process will be performed at National Agency for Quality Assurance of Higher Education. Realisation of summer school will follow accreditation process. During summer school a monitoring visit will be organised, by the delegation which will consist of at least one member from each consortium partner. Faculty of Maritime Studies has sent a letter to the rector of UoM, declaring its readiness to organise a summer school in English, named “Sustainability in Yachting and Cruise Tourism”: The same is expected from the Faculty of Tourism, for the organisation of summer school “Entrepreneurship in Heritage Tourism”.

## Slide 9
WP 5 - Quality Control and Monitoring
5.2 | Development and implementation of Internal Quality Control and Monitoring Plan | – | Nov. 2021 | All partners | QAB will continue to monitor and assess the quality of project activities and deliverables throughout the project period. The WP leader will prepare two annual QA reports. The draft of the first report, which covers the period of activities from the beginning of the project up to the end of the first year of the project, will be discussed at the meeting of the QAB which is supposed to be held until the end of November 2020 (and then the report will be finalised by the WP leader, then accepted by the QAB and submitted to the Project Management Board for final approval). The second annual report will be prepared at the last month of the project, covering the period from the end of the first year until the end of the project. Satisfaction surveys will be used regularly until the end of the project, elaborated by the WP leader. The data from surveys will be presented in the annual QA reports.

## Slide 10
5.3 | External Quality Control and Evaluation | Nov. 2020 | Dec. 2021 | All partners | External quality control and evaluation of the project will be carried out two times during the project lifetime, by experts engaged through an open call. The call for selection of evaluators is expected being published in December 2020 and the first evaluation is supposed to take place in January 2021, performing quality assessment of the first year of the project, while the second evaluation process will be completed at the end of the project. The evaluator will prepare evaluation reports, which will provide inputs for improving overall quality of the implementation, and for final report to be submitted to EACEA, and can also serve as background material for project exploitation plan.
5.4 | Impact Analysis | March 2021 | Oct. 2021 | All partners | Detailed impact analysis will be conducted towards the end of the project and completed by October 2021. The analysis will be used for the development of the Exploitation Roadmap and project final report.

## Slide 11
WP6 - Dissemination and Exploitation of Project Results
6.1 | Development and implementation of dissemination and exploitation plans | – | Nov. 2021 | All partners | Dissemination activities will continue throughout the project period. Dissemination and exploitation plan will be updated in the second year of the project implementation, due to the specific situation with COVID-19 pandemic and related restriction measures.
6.2 | Website of the project and social media accounts | – | Nov. 2021 | web network | Website of the project and social media accounts will be updated regularly.
6.3 | Dissemination products and materials | – | Nov. 2021 |  | New editions of the Newsletter will be published semi-annually, in accordance with the project plan. First procurement of promotional material should be launched soon and finalized until the end of December 2020. In addition to project promotional material, two types of institutional guides in English will be updated/developed: Guides for Incoming Students and Guides for Incoming Researchers.

## Slide 12
6.4 | Dissemination and exploitation events | – | Nov. 2021 |  | The situation with the COVID-19 pandemic makes it impossible to predict will there be live events organised, where the project could be presented. According to the project proposal, the following was foreseen: Events such as open days for students and wider public (M17, 1 day) and staff week for EU partner universities (M22, 2day) at each Montenegrin HEI (opportunity for networking and ensuring sustainability of project outcomes through new projects or possible establishment of double or joint degrees with EU partner HEIs. Round tables involving Montenegrin HEIs teaching staff, student parliament, scientific diaspora and wider public audience will be organized during these events. Consortium will also ensure that project benefits from different events organised by national stakeholders – ministries, agency and National Erasmus+ office as well (traditional Erasmus +Info Day at UoM, M12, M23). In particular, participation in annual Science Days (M11, M22) is envisaged as a place for promotion of IESP and HEIs, as well as continuation of participation in national and institutional events for promotion of educational offer (e.g. educational fairs). Most of these activities will be held online.

## Slide 13
6.5 | Development of exploitation roadmap | April 2021 | Nov. 2021 |  | Exploitation roadmap will be developed, providing a basis for the continuation of the project results after its completion. It will be developed during the project lifetime, based on the outcomes of the Impact Analysis.
6.6 | Exploring possibilities for continuation of the cooperation with the EU partners | – | Nov. 2021 |  | Back-to-back with the final project meeting, 4-hour session will be held, where conclusions on the future steps for the purpose of ensuring project sustainability will be drawn and incorporated into the final project report. In addition to these consultations, provided that there is interest in joint research and innovation activities, additional meetings can be organized during regular WP meetings.

## Slide 14
WP7 - Project Management
7.2 | Project meetings | – | Nov. 2021 | In Podgorica or on-line | By the project proposal, in the forthcoming period there should be one PMB meeting, at the end of the project. If necessary, the partners will organize other meetings.
7.3 | Day-to-day management of the project activities | – | Nov. 2021 | All partners | This activity will continue throughout the project period, in accordance with the plan and already established mechanisms and practice, which have shown to be efficient with regard to communication, administration and management. The project partners will submit to the PC semi-annual technical and financial reports.

## Slide 15
7.4 | Periodic and final reports to EACEA | Nov. 2020 | Jan. 2022 | UoM (on behalf of all partners) | The reports will be prepared according to the provisions of the Grant Agreement. The partners will provide all necessary information and reports to the PC in order to compile adequate reports to be sent to EACEA. External evaluation report (to be developed under the activity 5.3) and Impact Analysis (to be developed under the activity 5.4) will contribute to preparation of the final technical report. External audit report (to be developed under the activity 7.5) will contribute to preparation and will be a part of the final financial report.
7.5 | External financial control | Sept. 2021 | Dec. 2021 | All partners | In accordance with the EACEA rules, the PC will engage an external auditor who will conduct a financial audit of the project.