## Short term impact
Number | Description | Target groups/ | Quantitative indicators | Description | Value | No. of | No. of | Type: student (S); Staff (ST), Prof& | Achieved | link | Notes
|  | Potential benficiaries |  |  |  | attentants | Institutions | Research (PR), Public Admin (PA) | y (1)/n (0)/half (0,5)
1 | IESP network established and maintained | 1.1: MNEE HEIs management | I.1.1. At least 10 joint events(3 project meetings, trainings, dissemination) | 1 Face-to-face study meeting at UL (20-21 February, 2020) | 1 | 18 | 8 | ST, PR |  | http://www.iesp.ucg.ac.me/uploaded/files/IESP_Report%20on%20the%20study%20visit%20to%20the%20University%20of%20Ljubljana%281%29.pdf | The seminar was participated by the Slovenian Ministry of Education, Slovenian QA Agency,
|  | 1.2 MNE HEIs teaching/research staff |  | 1 On-line study meeting at UCA-F (June 3, 2020) | 1 | 21 | 6 | ST, PR, PA |  | https://www.iesp.ucg.ac.me/page.php?id=12
|  | 1.3. MNE HEIs IT and administrative staff |  | 1 On-line study meeting at UCA (July 24, 2020) | 1 | 21 | 7 | ST, PR, PA |  | https://www.iesp.ucg.ac.me/page.php?id=12
|  | 1.4. MNE HEIs students |  | 1 On line training on internationalisation on research at UCA-F (July 2020) | 1 | 27 | 4 | S, PR |  | http://www.iesp.ucg.ac.me/page.php?id=18
|  | 1.5. Public administration representatives |  | 1 On-line training on strategic planning by UL | 1 | 16 | 4 | ST, PR, PA |  | http://www.iesp.ucg.ac.me/page.php?id=18
|  | 1.6. EU universities' staff |  | 1 On-line training on summer school by UL (October 20, 2020) | 1 | 20 | 5 | ST, PR, PA |  | http://www.iesp.ucg.ac.me/page.php?id=20
|  | 1.7 International students |  | 1 On-line training on internationalisation of staff by UCA (October 22-23, 2020) | 1 | 58 | 19 | ST, PA |  | https://www.iesp.ucg.ac.me/page.php?id=12 | The seminar was open to KA107 partners of UCA; 15 instituions outside the consortium + 35 attendants
|  |  |  | 1 On-line training on summer school by UCA (November 9 & 11, 2020) | 1 | 31 | 5 | ST, PR, PA |  | https://www.iesp.ucg.ac.me/page.php?id=12
|  |  |  | 1 Study visit to UCA on May 2022 | 1 | 8 | 2 | PR
|  |  |  | 1 Kick-off meeting (January 15-16, 2020) | 1 | 24 | 10 | ST, PR, PA, S |  | https://www.iesp.ucg.ac.me/uploaded/files/Minutes%20of%20the%20Kick-off%20Meeting%283%29-1%281%29.pdf
|  |  |  | Project Management Board (PMB) meeting (May 18, 2020) | 1 | 14 | 8 | ST, PR, PA |  | https://www.iesp.ucg.ac.me/uploaded/files/IESP%20PMB%201st%20meeting%20Minutes%281%29.docx
|  |  |  | PMB meeting (November 13, 2020) | 1 | 18 | 9 | ST, PR, PA |  | https://www.iesp.ucg.ac.me/uploaded/files/Final%20-%20IESP%20PMB%202nd%20meeting%20Minutes%20-%20Copy%20-%20Copy%281%29.docx
|  |  |  | PMB meeting (February 25, 2021) | 1 | 11 | 7 | ST, PR, PA |  | https://www.iesp.ucg.ac.me/uploaded/files/IESP%20PMB%204th%20meeting%20Minutes%20final.docx
|  |  |  | Final PMB meeting (November 9-10, 2022) | 1 |  |  | ST, PR, PA |  | https://www.iesp.ucg.ac.me/page.php?id=12
|  |  |  | Quality Board (QB) online meeting (19/06/2020) | 1 | 8 | 8 | ST, PR, PA
|  |  |  | Quality Board (QB) online meeting (November/2022) | 1 |  | 9 | ST, PR, PA
|  |  | Total |  | 16 | 295 | 7.4 |  | 1.6
|  |  | I.1.2. 1 benchmark report | 1 benchmark report UoM | 1 |  | 2 | ST, PR |  | https://www.iesp.ucg.ac.me/uploaded/files/UoM%20Benchmarking%20-%20Final%20document.pdf
|  |  |  | 1 benchmark report UNIM | 1 |  | 2 | ST, PR |  | UDG Benchmark report has not been uploaded by their request (available at the intranet of IESP webpage)
|  |  |  | 1 benchmark report UDG | 1 |  | 2 | ST, PR |  | https://www.iesp.ucg.ac.me/uploaded/files/University%20Mediterranean%20-%20Benchmarking%20analysis.pdf
|  |  | Total |  | 3 |  | 2 |  | 3
|  |  | I.1.3. 1 impact analysis | 1 impact analysis to be delivered (end of project) | 1 |  | 9 | ST, PR | 1 | https://www.iesp.ucg.ac.me/page.php?id=12
|  |  | Total |  | 1 |  | 9 |  | 1
|  |  | I.1.4. 2 external evaluation reports | 1 first external evaluation report | 1 |  | 9 | ST, PR |  | https://www.iesp.ucg.ac.me/uploaded/files/IESP-QE-final.pdf
|  |  |  | Final external evaluation report | 1 |  | 9 | ST, PR |  | To be uploaded at the end of the project
|  |  | Total |  | 2 |  | 9 |  | 1 | https://www.iesp.ucg.ac.me/page.php?id=12
|  |  | I.1.5. 2 project reports | 1 Review on EU HEIs models (WP1) | 1 |  | 3 | ST, PR |  | https://www.iesp.ucg.ac.me/uploaded/files/Review%20on%20EU%20HEIs%20models%20of%20legal%20and%20administrative%20framework%20in%20regard%20to%20interna tionalization%20of%20education%20FINALE%285%29%281%29.pdf
|  |  |  | 1 First report on procurement of equipment (WP2) | 1 |  |  | ST, PR |  | https://www.iesp.ucg.ac.me/uploaded/files/Dev.%202.1%20Procurement%20of%20equipment%20for%20supporting%20internationalization%20-%201%20st%20report.docx
|  |  |  | 1 report on the state-of-the-art of redesign of websites in English (WP2) | 1 |  | 3 | ST, PR |  | https://www.iesp.ucg.ac.me/uploaded/files/Report%20-%202.2%20Development-Redesign%20of%20English%20web%20sites%20of%20Montenegrin%20HEIs.docx
|  |  |  | 1 report on the online workshop on strategic planning (UL; 16&18 July, 2020) (WP2) | 1 |  | 4 | ST, PR |  | https://www.iesp.ucg.ac.me/uploaded/files/Minutes-Workshop-Strategic%20planning-16%20and%2018%20June%202020.pdf
|  |  |  | 1 report on the online training internationalisation on research and innovation (UCA-F; 16&18 July, 2020) (WP2) | 1 |  | 4 | ST, PR |  | https://www.iesp.ucg.ac.me/uploaded/files/Final%20report%202.3.2%281%29.docx
|  |  |  | 1 report on the on-line training on summer Schools by UL (WP3) | 1 |  | 2 | ST, PR |  | https://www.iesp.ucg.ac.me/uploaded/files/2.3%20On-line%20Training%20on%20Summer%20Schools%20organized%20by%20the%20University%20of%20Ljubljana%20-%20report%281%29.docx
|  |  |  | 1 report on the online training of Staff by UCA | 1 |  | 7 | ST, PR |  | https://www.iesp.ucg.ac.me/uploaded/files/3.3.4%20Report%281%29.docx
|  |  | Total |  | 7 |  | 3.8333 |  | 3.5
2 | Enhanced capacities for training Strategic planning and university governance | 2.1 MNE HEIs managment | I.2.1 at least 2 types of trainings organised for management, teaching and administratives staff | Trainining on Summer Schools | 2 | 78 | 5 | ST, PR, PA
|  | 2.2 MNE HEIs teaching/research staff |  | Training on Internationalisation of research | 1 | 27 | 4 | S, ST, PR |  | https://www.iesp.ucg.ac.me/page.php?id=12
|  | 2.3 MNE HEIs IT and administrative staff |  | Training on internationalisation for staff | 1 | 58 | 19 | ST, PR |  | https://www.iesp.ucg.ac.me/page.php?id=12
|  | 2.4 Public administration representatives |  | Training on strategic planning of internationalisation | 1 | 16 | 4 | ST, PR, PA |  | https://www.iesp.ucg.ac.me/page.php?id=12
|  |  | Total |  | 5 | 179 | 6.4048 |  | 2.5 | All MNE HEIs participated
|  |  | I.2.2 at least 20 participants trained |  |  | 179
|  |  | Total |  | 7 | 179 | 6.4048 |  | 8.95 | It is difficult to say how many participants are repeated, but the minimum number per type of training is 16 and the targets are different
|  |  | I.2.3 at least 100 computers purchased | Number of computers |  | 100 | 3
|  |  | Total |  |  | 100 | 3 |  | 1 | Equipment has been installed in all three MNE HEIs
3 | Strategic framework for internationalisation enhanced | MNE HEIs | I3.1 Three strategic documents developed | 1 Guidelines for Internationalisation of Montenegrin Universities | 1 |  | 3 |  |  | https://www.iesp.ucg.ac.me/uploaded/files/Guidlines%20for%20internationalisation%20of%20Montenegrin%20universities.pdf
|  |  |  | 1 UoM Internationalisation Strategy-ENG | 1 |  | 1 |  |  | https://www.iesp.ucg.ac.me/uploaded/files/IESP%20-%20Internationalisation%20Strategy%20of%20UoM%202021-2026.pdf
|  |  |  | 1 UoM Internationalisation Strategy-MN | 1 |  | 1 |  |  | https://www.iesp.ucg.ac.me/uploaded/files/IESP%20-%20Strategija%20internacionalizacije%20UCG%202021-2026.pdf
|  |  |  | 1 UDG Internationalisation Strategy-ENG | 1 |  | 1 |  |  | https://www.iesp.ucg.ac.me/uploaded/files/strategija_jan21Ver2.pdf
|  |  |  | 1 UNIM Internationalisation Strategy-ENG | 1 |  | 1 |  |  | https://www.iesp.ucg.ac.me/uploaded/files/UM_Internationalization%20Strategy%202021-2026_F.pdf
|  |  | Total |  | 5 | 0 | 1.4 |  | 1.6667 | All Universities developed and adopted their respective Strategic Plans
|  |  | I.3.2 Three action plants developed | 1 UoM Internationalisation Strategy-ENG | 1 |  | 1 |  |  | https://www.iesp.ucg.ac.me/uploaded/files/IESP%20-%20Internationalisation%20Strategy%20of%20UoM%202021-2026.pdf
|  |  |  | 1 UDG Internationalisation Strategy-ENG | 1 |  | 1 |  |  | https://www.iesp.ucg.ac.me/uploaded/files/strategija_jan21Ver2.pdf
|  |  |  | 1 UNIM Internationalisation Strategy-ENG | 1 |  | 1 |  |  | https://www.iesp.ucg.ac.me/uploaded/files/UM_Internationalization%20Strategy%202021-2026_F.pdf
|  |  | Total |  | 3 | 0 | 1 |  | 1
|  |  | I.3.3 Three sets of supporting documents developed | One set of UoM | 1 |  | 1 |  |  | http://www.iesp.ucg.ac.me/page.php?id=12
|  |  |  | One set of UNIM | 1 |  | 1 |  |  | http://www.iesp.ucg.ac.me/page.php?id=12
|  |  |  | One set of UDG | 1 |  | 1 |  |  | http://www.iesp.ucg.ac.me/page.php?id=12
|  |  | Total |  | 3 | 0 | 1 |  | 1
|  |  | I.3.4 Three bodies for evaluation of the strategy implementation established | UoM
|  |  |  | UNIM | 1 |  | 1 |  |  | UNIM established the Internationalization Strategy Implementation Committee in 2022
|  |  |  | UDG | 3 |  | 1 |  |  | UDG established three Boards/Collegiums that will evaluate implementation in the field and provide report to UDG Senate: Collegium for research/internationalization; Collegium for Alumni Association;Collegium for Entrepreneurship
|  |  | Total |  | 4 | 0 | 1 |  | 1.3333
|  |  | I.3.5 Three evaluation reports adopted | UoM
|  |  |  | UNIM | 1 |  |  |  |  | UNIM adopted the evaluation report
UDG
|  |  | Total |  | 1 | 0 | #DIV/0! |  | 0.33333
4 | Teaching in English improved | MNE HEIs teaching/research staff | I.4.1 At least 250 courses available in English | University of Montenegro, Faculty of Architecture | 28 |  | 1 |  |  | https://www.ucg.ac.me/objava/blog/19379/objava/120061-faculty-of-architecture
|  | MNE HEIs students |  | University of Montenegro, Biotechnical Faculty | 11 |  | 1 |  |  | https://www.ucg.ac.me/objava/blog/19379/objava/120063-biotechnical-faculty
|  | Incoming students |  | University of Montenegro, Faculty of Electrical Engineering | 2 |  | 1 |  |  | https://www.ucg.ac.me/objava/blog/19379/objava/120064-faculty-of-electrical-engineering
|  | Incoming staff |  | University of Montenegro, Faculty of Dramatic Arts | 19 |  | 1 |  |  | https://www.ucg.ac.me/objava/blog/19379/objava/120065-faculty-of-dramatic-arts
|  |  |  | University of Montenegro, Faculty of Fine Arts | 15 |  | 1 |  |  | https://www.ucg.ac.me/objava/blog/19379/objava/120066-faculty-of-fine-arts
|  |  |  | University of Montenegro, Faculty for Sport and Physical Education | 2 |  | 1 |  |  | https://www.ucg.ac.me/objava/blog/19379/objava/120067-faculty-for-sport-and-physical-education
|  |  |  | University of Montenegro, Faculty of Phylology | 39 |  | 1 |  |  | https://www.ucg.ac.me/objava/blog/19379/objava/120068-faculty-of-philology
|  |  |  | University of Montenegro, Faculty of Civil Engineering | 32 |  | 1 |  |  | https://www.ucg.ac.me/objava/blog/19379/objava/120069-faculty-of-civil-engineering
|  |  |  | University of Montenegro, Faculty of Metallurgy and Technology | 2 |  | 1 |  |  | https://www.ucg.ac.me/objava/blog/19379/objava/120070-faculty-of-metalurgy-and-technology
|  |  |  | Music Academy | 59 |  | 1 |  |  | https://www.ucg.ac.me/objava/blog/19379/objava/120071-music-academy
|  |  |  | University Mediterranean | 48 |  | 1 |  |  | https://unimediteran.net/subjects-in-english/?lang=en
|  |  |  | University Donja Gorica | 120 |  | 1 |  |  | https://www.udg.edu.me/uploads/newsarticles/42dd1216a11c7b32698bc10069063aa1.pdf
|  |  | Total |  | 377 | 0 | 1 |  | 1.508
|  |  | I.4.2 Two summer school curricula developed and implemented | "Sustainable development of yatching and cruise industry" | 1 | 20 |  |  |  | https://dwm.prz.edu.pl/fcp/aGBUKOQtTKlQhbx08SlkTVgJQX2o8DAoHNiwFE1xVSHxBG1gnBVcoFW8SETZKHg/56/code_4DlgUIg9YPBJhAAQqEk1UB0FcAyQ/aktualnosci/summer_school_kotor.pdf
|  |  |  | "Entrepreneurship in heritage tourism" | 1 | 20 |  |  |  | https://www.iesp.ucg.ac.me/uploaded/files/Report%20on%20Summer%20School%20Entrepreneurship%20in%20Heritage%20Tourism%20%282%29.pdf
|  |  | Total |  | 2 | 40 | 1 |  | 1
|  |  | I.4.3 At least 78 hours of English course for teaching purposes held | Online training on design of courses on English language | 5 | 27 | 4 |  |  | https://dwm.prz.edu.pl/fcp/aGBUKOQtTKlQhbx08SlkTVgJQX2o8DAoHNiwFE1xVSHxBG1gnBVcoFW8SETZKHg/56/code_4DlgUIg9YPBJhAAQqEk1UB0FcAyQ/aktualnosci/summer_school_kotor.pdf
|  |  |  | Workshop: Design of catalogues for courses offered in English (UL) | 4.5 |  |  |  |  | https://www.uni-lj.si/study/news/project-iesp/ (https://urldefense.com/v3/__https://www.uni-lj.si/study/news/project-iesp/__;!!D9dNQwwGXtA!SUrxnQliFNZaKcEptw9i3lxLT3Pvr4xOXGnrgvh6_yIaDGaQ74HNh543jsgu5UBxO_sbgn1WSej_MF77Sa0BAisM_EUwDA$).
|  |  | Total |  | 9.5 | 27 | 4 |  | 0.12179 | Other courses?
5 | Capacities for internationalisation increased | Teaching/Research staff at MNE HEIs | I.5.1 Three Language support centres with 4 classrooms established and operational | Decission of establishing Language support centre at UoM | 1 |  | 1 |  |  | https://www.iesp.ucg.ac.me/uploaded/files/02-401-1-%20Decision%20on%20establishment%20of%20Languge%20Centre%20-%20UoM.pdf
|  | IT and administrative staff at MNE HEIs |  | Language support centre at UNIM | Not reported |  | 0
|  |  |  | Language support centre at UDG | 1 |  | 1 |  |  | https://www.iesp.ucg.ac.me/uploaded/files/Decison%20on%20Establishment%20of%20language%20centre%20-%20UDG.pdf
|  |  | Total |  | 2 | 0 | 0.5 |  | 0.66667
|  |  | I.5.2 Three sets of documents for internationalisation support developed and utilized | One set of UoM | 1 |  | 1 |  |  | http://www.iesp.ucg.ac.me/page.php?id=12
|  |  |  | One set of UNIM | 1 |  | 1 |  |  | http://www.iesp.ucg.ac.me/page.php?id=12
|  |  |  | One set of UDG | 1 |  | 1 |  |  | http://www.iesp.ucg.ac.me/page.php?id=12
|  |  | Total |  | 3 | 0 | 1 |  | 1
|  |  | I.5.3 At least 4 types of trainings organised | Training for internationalisation of research (UCA-F) | 1 | 27 | 4 | S, ST, PR |  | https://www.iesp.ucg.ac.me/page.php?id=12
|  |  |  | Training in summer schools (UL + UCA) | 2 | 51 | 5 | ST, PR, PA |  | https://www.iesp.ucg.ac.me/gallery.php?id=52 | http://www.iesp.ucg.ac.me/page.php?id=12
[8 empty] | ST, PR, PA |  | https://www.iesp.ucg.ac.me/page.php?id=12
|  |  |  | Training in internationalisation of Staff | 1 | 58 |  | ST, PR, PA |  | https://www.iesp.ucg.ac.me/page.php?id=12
|  |  |  | Training on strategic planning (UL) | 1 | 16 | 4 | ST, PR, PA |  | https://www.iesp.ucg.ac.me/gallery.php?id=47
|  |  |  | Workshop on interculturality in HE organized for MN staff (3-4 June, 2021) | 1 | 7 | 4 | ST |  | http://www.iesp.ucg.ac.me/news.php?id=32
|  |  |  | 1 on line training on design of Courses in English Language (UL) | 1 | 27 | 4 | ST, PR |  | http://www.iesp.ucg.ac.me/news.php?id=25
|  |  | Total |  | 6 | 186 | 4 |  | 1.5
|  |  | I.5.4 At least 40 people trained |  |  | 186
|  |  | Total |  |  | 186 | 4 |  | 4.65
|  |  | I.5.5 Two or three types of guides for incoming mobility developed | UoM guide
UDG guide
UM guide
|  |  | Total |  | 0 | 0 | #DIV/0! |  | 0 | Cannot find links to the guides, if they existed or have been published in the respective webs
|  |  | I.5.6 At least 78 hours of English course for teaching purpose held | 1 on line training on design of Courses in English Language (UL) | 4.5 | 27 | 4 |  |  | https://www.iesp.ucg.ac.me/gallery.php?id=58
|  |  |  | Know-how transfer related to improving English skills of teaching staff | 5 | atendants?? | ??? |  |  | https://www.iesp.ucg.ac.me/gallery.php?id=65
|  |  | Total |  | 9.5 | 27 | #DIV/0! |  | 0.12179
|  |  | I.5.7 Three international relations offices strenghtened |  | 3 | 3 | 3 | ST
|  |  | Total |  | 12.5 | 3 | 3 |  | 4.1667 | All three IROs were strenghtened as a result of the know transfer and CB process
|  |  | I.5.8 Number of administrative staff involved in internationalisation issues increased by at least 10% |  | 2019 | 2022 | Increase (%)
|  |  |  | UoM | 3 | 9 | 200
|  |  |  | UDG | 7 | 17 | 142.8571
|  |  |  | UM | 2 | 5 | 150
|  |  | Total |  | 12 | 31 | 164.2857 |  | 16.4286
6 | Visibility for different modalities and competitiveness of HEIs increased | MNE HEIs | I.6.1 Three institutional web pages in English redesigned/developed and maintained | UoM | 1 |  | 8 |  |  | https://www.ucg.ac.me/
|  | Incoming students |  | UDG | 1 |  | 1 |  |  | https://www.udg.edu.me/en/
|  | Incoming staff |  | UM | 1 |  | 1 |  |  | https://unimediteran.net/?lang=en
|  |  | Total |  | 3 | 0 | 4.5 |  | 1
|  |  | I.6.2 Number of existing profiles at national portal, Naucna mreza, increased by 10% |  | 2019 | 2022 | Increase (%)
UoM
|  |  |  | UNIM | 7 | 11 | 57.1429
UDG guide
Total
|  |  | I.6.3 Number of profiles at free-of-charge global databases increased by 10% |  | 2019 | 2022 | Increase (%)
|  |  |  | UNIM | 3 | 6 | 100
UDG
Total
|  |  | I.6.4 Increased number of incoming students by 20% |  | 2019 | 2022 | Increase (%) |  |  | 20% not originally included in the project. It has been set to 20% here by similarity
|  |  |  | UoM | 48 | 85 | 77.0833 |  |  | with the long-term impact goal for the same indicator
|  |  |  | UNIM | 1 | 2 | 100
|  |  |  | UDG | 2 | 7 | 250
|  |  | Total |  | 51 | 94 | 142.3611 |  | 7.1181
|  |  | I.6.5 Increased number of incoming staff by 20% |  | 2019 | 2022 | Increase (%) |  |  | 20% not originally included in the project. It has been set to 20% here by similarity
|  |  |  | UoM | 49 | 320 | 553.0612
|  |  |  | UNIM | 18 | 32 | 77.7778
|  |  |  | UDG | 8 | 36 | 350
|  |  | Total |  | 75 | 388 | 326.9463 |  | 16.3473
Note on K101: Ana: the same as previous comment

## Long term impact
Number | Description | Target groups/ | Quantitative indicators | Description | Value | No. of | No. of | Type: student (S); Staff (ST), Prof& | Achieved | Evidence | link | Notes
|  | Potential benficiaries |  |  |  | attentants/partners | Institutions | Research (PR), Public Admin (PA) | y (1)/n (0)/half (0,5)
1 | IESP network continued | 1.1 MNE HEIs management | I.7.1. at least 2 new joint proposals within different programmes | Erasmus+ CBHE project MES&P: "Development of a regional Joint Master Program in Maritime Environmental Protection Management | 1 |  | 9 | ST, PR, PA, S |  | Project No. 619239-EPP-1-2020-1-ME-EPPKA2-CBHE-JP | https://www.mepm.ucg.ac.me/
|  | 1.2. MNE HEIs academic/research staff | (projects should include at least two partners of IESP consortium) | Erasmus+ CBHE project AL4All "Western Balkan entrepreneurial university alliances – keeping in touch for lifelong relations" | 1 |  |  |  |  | Coordinated by UoM |  | with participation of the European partners of IESP and Universities and institutions of Albania
|  | 1.3. MNE HEIs administrative staff |  | Opening of the Project Office for International projects at UoM (April, 2022) | 1 |  | 1 | S, ST, PR, PA |  | The new office willsupport the application and management of International project and boost the participacion in new calls
|  | 1.4. MNE HEIs students |  | Erasmus+ CBHE project "Digital Entrepreneurial Nest and Industry 4.0 in Montenegro (DigN€st)" | 1 |  | 7 | S, ST, PR, PA |  | Project No.: 619099-EPP-1-2020-1-ME-EPPKA2-CBHE-JP | https://dignest.me/#/ | particicpated by UoM and partners from 5 EU countries including Slovenia
|  | 1.5. Government partners | [7 empty] | Coordinated by UDG
|  |  | Total |  | 4 | 0 | 5.6667 |  | 2
|  |  | I.7.2 At least three new cooperation protocols | UoM
UDG
UM
|  |  | Total |  | 0 | 0 | #DIV/0! |  | 0
2 | IESP strategies implementation continued and strategic planning process enhanced | 1. MNE HEIs management | I.8.1 At least 3 implementation and evaluation reports available, at least mid-term and final | Procurement of equipment for supporting internatinalisation (first report) | 1 |  | 4 | ST, PR, PA |  | https://www.iesp.ucg.ac.me/uploaded/files/Dev.%202.1%20Procurement%20of%20equipment%20for%20supporting%20internationalization%20-%201%20st%20report.docx
|  | 2. MNE HEIs academic/research staff |  | Procurement of equipment for supporting internatinalisation (final report) | 1 |  | 4 | ST, PR, PA |  | Pending to be uploaded on the web
|  | 3. MNE HEIs administrative staff |  | First year report to the EACEA | 1 |  | 9 | ST, PR, PA |  | Pending to be uploaded on the web
|  | 4. MNE HEIs students |  | Final project report to the EACEA | 1 |  | 9 | ST, PR, PA |  | Pending to be uploaded on the web upon approval by the PMB
|  | 5. Government partners |  | 1 report on the state-of-the-art of redesign of websites in English (WP2) | 1 |  | 3 | ST, PR |  | https://www.iesp.ucg.ac.me/page.php?id=12
|  |  |  | First internal QA report | 1 |  | 9 | ST, PR, PA |  | Pending to be uploaded on the web
|  |  |  | Final internal QA report | 1 |  | 9 | ST, PR, PA |  | To be uploaded upon completion of the project and approval by the PMB
|  |  |  | External Quality Control Evaluation | 1 |  | 9 | ST, PR, PA |  | https://www.iesp.ucg.ac.me/uploaded/files/IESP-QE-final.pdf
|  |  |  | Study of impact | 1 |  | 9 | ST, PR, PA |  | To be uploaded upon completion of the project and approval by the PMB
|  |  | Total |  | 9 | 0 | 7.2222 |  | 3
|  |  | I.8.2 At least 3 drafts of renewed internationalisation strategies developed | 1 Guidelines for Internationalisation of Montenegrin Universities | 1 |  | 3 |  |  | https://www.iesp.ucg.ac.me/uploaded/files/Guidlines%20for%20internationalisation%20of%20Montenegrin%20universities.pdf
|  |  | Total |  | 1 | 0 | 3 |  | 0.33333
|  |  | I.8.3 At least three new strategic documents drafted | 1 UoM Internationalisation Strategy-ENG | 1 |  | 1 |  |  | https://www.iesp.ucg.ac.me/uploaded/files/IESP%20-%20Internationalisation%20Strategy%20of%20UoM%202021-2026.pdf
|  |  |  | 1 UoM Internationalisation Strategy-MN | 1 |  | 1 |  |  | https://www.iesp.ucg.ac.me/uploaded/files/IESP%20-%20Strategija%20internacionalizacije%20UCG%202021-2026.pdf
|  |  |  | 1 UDG Internationalisation Strategy-ENG | 1 |  | 1 |  |  | https://www.iesp.ucg.ac.me/uploaded/files/strategija_jan21Ver2.pdf
|  |  |  | 1 UM Internationalisation Strategy-ENG | 1 |  | 1 |  |  | https://www.iesp.ucg.ac.me/uploaded/files/UM_Internationalization%20Strategy%202021-2026_F.pdf
|  |  | Total |  | 5 | 0 | 4 |  | 1.6667 | Both indicators (I.8.2 and I.8.3) have been summed up here as they refer to the same documents
3 | Internationalisation at MNE HEIs additionally improved | 1. MNE HEIs management | I.9.1 Number of new international projects (education, collaborative research, technology transfer within the MNE region) | UoM new international projects from 2020 to date | 42 |  |  |  |  | https://www.ucg.ac.me/projektiSveJedinice.php | I counted only those funded by international calls. Please, check. Include total number of partners
|  | 2. MNE HEIs academic/research staff |  | UDG new international projects from 2020 to date | 20 |  |  |  |  | https://www.udg.edu.me/en/research-and-projects | I have not included Erasmus mobility because I could not find them. Please count and update. Include total number of partners
|  | 3. MNE HEIs administrative staff |  | UNIM new international projects from 2020 to date | 9 |  |  |  |  | http://unimediteran.net/colaboration/projects/?lang=en | I have not included Erasmus mobility because I could not find them. Please count and update. Also, include those project that started on 2020 and are already finished. Include also total number of partners
|  | 4. MNE HEIs students | Total |  | 77 | 0 | 0 |  | 77
|  | 5. Public administration representatives | I.9.2 Increased participation in mobility programmes by at least 30% |  | 2019 | 2022 | Increase (%)
UoM increase
UDG increase
|  |  |  | UM increase | 8 | 14 | 75
|  |  | Total |  | 8 | 14 | 75 |  | 7.5
|  |  | I.9.3 Increased number of cooperation protocols by 20% |  | 2019 | 2022 | Increase (%)
UoM increase
|  |  |  | UDG increase | 23 | 36 | 56.5217
|  |  |  | UM increase | 6 | 16 | 166.6667
|  |  | Total |  | 29 | 52 | 111.5942 |  | 5.5797
4 | Quality of teaching process further improved | 1. MNE HEIs | I.10.1 Courses in English as part of regular teaching process maintained | UoM courses | 209 |  | 1 |  |  | https://www.iesp.ucg.ac.me/uploaded/files/List%20of%20available%20subjects%20in%20English%20language%283%29.xlsx
|  | 2. Incoming students |  | UDG courses | 120 |  | 1 |  |  | https://www.udg.edu.me/uploads/newsarticles/42dd1216a11c7b32698bc10069063aa1.pdf
|  | 3. Incoming staff |  | UM courses | 48 |  | 1 |  |  | https://unimediteran.net/subjects-in-english/?lang=en
|  |  | Total |  | 377 | 14 | 1 |  | 1
|  |  | I.10.2 Additional number of courses in English available (at least 15% more) |  | 2022 | 2022 | Increase
|  |  |  | UoM courses | 209 | 209 | 0
|  |  |  | UDG courses | 120 | 120 | 0
|  |  |  | UM courses | 48 | 48 | 0
|  |  | Total |  | 377 | 377 | 0 |  | 0
|  |  | I.10.3 At least three series of training in Montenegrin for foreign students held | UoM ME courses |  |  | 1
|  |  |  | UDG ME courses | 1 | 2 | 1 |  |  | At Center for Foreign Languages UDG orginize course of Montenegrin for foreign students
|  |  |  | UNIM MN courses | 1 | 5 | 1
|  |  | Total |  | 2 | 7 | 1 |  | 0.66667
|  |  | I.10.4 At least 10 series of trainings of English for specific purposes organized | UoM courses
|  |  |  | UDG courses | 1 | 30 | 1 |  |  | Organized "Academic English and English as Medium of Instruction - EMI” for teaching, “Business English” for administrative staff of the University.
|  |  |  | UM courses | 2 | 30 | 1
|  |  | Total |  | 3 | 60 | 1 |  | 1
5 | Incoming mobility increased | 1. MNE HEIs | I.11.1 At least 6 mobility network partnerships renewed/established | UoM
|  | 2. Incoming students |  | UDG | 36
|  | 3. Incoming staff |  | UNIM | 16 |  | 16
|  |  | Total |  | 57 | 5 | 16 |  | 9.5
|  |  | I.11.2 Number of incoming students increased by 20% |  | 2019 | 2022 | Increase
|  |  |  | UoM | 48 | 85 | 77.0833
|  |  |  | UDG | 0 | 5
|  |  |  | UNIM | 1 | 2 | 100
|  |  | Total |  | 49 | 92 | 88.5417 |  | 4.4271
|  |  | I.11.3 Number of outgoing students increased by 30% |  | 2019 | 2022 | Increase
|  |  |  | UoM | 138 | 204 | 47.8261
|  |  |  | UDG | 6 | 46 | 666.6667
|  |  |  | UNIM | 9 | 15 | 66.6667
|  |  | Total |  | 153 | 265 | 260.3865 |  | 8.6795
|  |  | I.11.4 Number of incoming teachers/researchers increased by 15% |  | 2019 | 2022 | Increase
|  |  |  | UoM | 49 | 320 | 553.0612
|  |  |  | UDG | 18 | 36 | 100
|  |  |  | UM | 6 | 18 | 200
|  |  | Total |  | 73 | 374 | 284.3537 |  | 18.9569
|  |  | I.11.5 Number of outgoing researchers increased by 20% |  | 2019 | 2022 | Increase
|  |  |  | UoM | 56 | 231 | 312.5
|  |  |  | UDG | 0 | 7
|  |  |  | UM | 19 | 29 | 52.6316
[5 empty] | 75 | 267 | 182.5658 |  | 9.1283
6 | International visibility of Montenegrin HEIs increased | MNE HEIs | I.12.1 Number of inter-institutional cooperation protocols improved by 20% |  | 2019 | 2022 | Increase
|  |  |  | UoM |  |  | 41.67
|  |  |  | UDG | 23 | 36 | 56.5217
|  |  |  | UNIM | 6 | 16 | 166.6667
|  |  |  | ACQAHE | 0 | 1 | 100 |  |  | ACQAHE-Navkis (Slovenian Quality Assurance Agency) MoU
|  |  | Total |  | 29 | 53 | 91.2146 |  | 4.5607
|  |  | I.12.2 Number of profiles in national databases increased by another 10% |  | 2019 | 2022 | Increase
|  |  |  | UoM |  |  | #DIV/0!
|  |  |  | UDG |  |  | #DIV/0!
|  |  |  | UNIM | 7 | 11 | 57.1429
|  |  | Total |  | 7 | 11 | 57.1429 |  | 5.7143
|  |  | I.12.3 Number of profiles at international databases increased by another 10% |  | 2019 | 2022 | Increase
|  |  |  | UoM |  |  | #DIV/0!
|  |  |  | UDG |  |  | #DIV/0!
|  |  |  | UM | 3 | 5 | 66.6667
|  |  | Total |  | 3 | 5 | 66.6667 |  | 6.6667
|  |  | I.12.4 Ranking of MNE HEIs in international lists improved |  | 2019 | 2022 | Increase
|  |  |  | UoM | In 2019 | in 2022 | #VALUE!
|  |  |  | UDG | In 2019 | in 2022 | #VALUE!
|  |  |  | UM | In 2019 | in 2022 | #VALUE!
[5 empty] | 0 | 0 | #VALUE! |  | #VALUE!
|  |  | I.12.5 Participation of MNE HEIs in international education and RTDI programmes increased |  | 2019 | 2022 | Increase
|  |  |  | UoM | In 2019 | in 2022 | #VALUE!
|  |  |  | UDG | In 2019 | in 2022 | #VALUE!
|  |  |  | UM | In 2019 | in 2022 | #VALUE!
[5 empty] | 0 | 0 | #VALUE! |  | #VALUE!

## Overall values
Short-term impact
Indicator | Description | Absolute value | Normalized value
I.1.1 | At least 10 joint events(3 project meetings, trainings, dissemination) | 16 | 1.6
I.1.2 | Benchmark report | 3 | 3
I.1.3 | 1 impact analysis to be delivered (end of project) | 1 | 1
I.1.4 | 2 external evaluation reports | 2 | 1
I.1.5 | 2 project reports | 7 | 3.5
I.2.1 | at least 2 types of trainings organised for management, teaching and administratives staff | 5 | 2.5
I.2.2 | at least 20 participants trained | 179 | 8.95
I.2.3 | at least 100 computers purchased | 100 | 1
I.3.1 | Three strategic documents developed | 5 | 1.6667
I.3.2 | Three action plans developed | 3 | 1
I.3.3 | Three sets of supporting documents developed | 3 | 1
I.3.4 | Three bodies for evaluation of the strategy implementation established | 4 | 1.3333
I.3.5 | Three evaluation reports adopted | 1 | 0.33333
I.4.1 | At least 250 courses available in English | 377 | 1.508
I.4.2 | Two summer school curricula developed and implemented | 2 | 1
I.4.3 | At least 78 hours of English course for teaching purposes held | 9.5 | 0.12179
I.5.1 | Three Language support centres with 4 classrooms established and operational | 2 | 0.66667
I.5.2 | Three sets of documents for internationalisation support developed and utilized | 3 | 1
I.5.3 | At least 4 types of trainings organised | 6 | 1.5
I.5.4 | At least 40 people trained | 186 | 4.65
I.5.5 | Two or three types of guides for incoming mobility developed | 0 | 0
I.5.6 | At least 78 hours of English course for teaching purpose held | 9.5 | 0.12179
I.5.7 | Three international relations offices strenghtened | 12.5 | 4.1667
I.5.8 | Number of administrative staff involved in internationalisation issues increased by at least 10% | 164.2857 | 16.4286
I.6.1 | Three institutional web pages in English redesigned/developed and maintained | 3 | 1
I.6.2 | Number of existing profiles at national portal, Naucna mreza, increased by 10% | 0 | 0
I.6.3 | Number of profiles at free-of-charge global databases increased by 10% | 0 | 0
I.6.4 | Increased number of incoming students | 142.3611 | 7.1181
I.6.5 | Increased number of incoming staff | 326.9463 | 16.3473
| Indicators > 1 |  | 14
| Indicators = 1 |  | 8
| Total |  | 22 | 75.8621
| Indicatos <1 |  | 7
| Average |  | 2.8797
Long-term impact |  |  |  | Average by
Indicator | Description | Absolute value | Normalized value | section
I.7.1 | At least 2 new joint proposals within different programs (projects should include at least two partners of IESP consortium). | 4 | 2
I.7.2 | At least 3 new cooperation protocols. | 0 | 0 | 1
I.8.1 | At least 3 implementation and evaluation reports available, at least mid-term and final. | 9 | 3
I.8.2 | At least 3 drafts of renewed internationalisation strategies developed. | 1 | 0.33333
I.8.3 | At least three new strategic documents drafted. | 5 | 1.6667 | 1.6667
I.9.1 | Number of new international projects (education, collaborative research, technology transfer within the MNE region). | 77 | 1
I.9.2 | Increased participation in mobility programmes by at least 30%. | 8 | 7.5
I.9.3 | Increased number of cooperation protocols by 20%. | 29 | 5.5797 | 4.6932
I.10.1 | Courses in English as part of regular teaching process maintained. | 377 | 1
I.10.2 | Additional number of courses in English available (at least 15% more). | 0 | 0
I.10.3 | At least three series of training in Montenegrin for foreign students held. | 2 | 0.66667
I.10.4 | At least 10 series of trainings of English for specific purposes organized. | 3 | 1 | 0.66667
I.11.1 | At least 6 mobility network partnerships renewed/established. | 57 | 9.5
I.11.2 | Number of incoming students increased by 20%. | 88.5417 | 4.4271
I.11.3 | Number of outgoing students increased by 30%. | 260.3865 | 8.6795
I.11.4 | Number of incoming teachers/researchers increased by 15%. | 284.3537 | 18.9569
I.11.5 | Number of outgoing researchers increased by 20%. | 182.5658 | 9.1283 | 10.1384
I.12.1 | Number of inter-institutional cooperation protocols improved by 20%. | 91.2146 | 4.5607
I.12.2 | Number of profiles in national databases increased by another 10%. | 57.1429 | 5.7143
I.12.3 | Number of profiles at international databases increased by another 10%. | 66.6667 | 6.6667
I.12.4 | Ranking of MNE HEIs in international lists improved. | #VALUE! | #VALUE!
I.12.5 | Participation of MNE HEIs in international education and RTDI programmes increased. | #VALUE! | #VALUE! | 5.6472
| Indicators > 1 |  | 13
| Indicators = 1 |  | 3
| Total |  | 16 | 72.7273
| Indicatos <1 |  | 4
| No data |  | 2 | (*) Indicator I.9.1 has beenarbitrary given a value of "1" (achieved) as there was no value set as a goal for it.
Average