## Slide 1: IESP PMB meeting Project activities completed in II project year
University of Montenegro
This project has been funded with support from the European Commission. This presentation reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein.

## Slide 2
WP2 - Capacity Building for Internationalization through staff training and equipment upgrade
2.2 | Development/redesign of English web sites of Montenegrin HEIs | Redesign finished
2.3 | Know-how transfer to teaching staff related to the internationalization | A2.3.3 – Know-how transfer related to improving English skills of teaching staff for delivering courses in English – courses organized at three Montenegrein HEIs
Additional trainings organized by UL | Know-how transfer to teaching staff related to the internationalization | Workshop “Interculturality in Higher Education” 3-4 June Workshop “Teaching multicultural groups of students in HE settings” 19 and 21 April Online Training on “Design of Courses in English Language” 2 and 5 March

## Slide 3
WP 3 - Development of Tools for Enhanced Internationalization
3.1 | Development of internationalization strategies and action plans | Internationalization Strategies of 3 Montenegrin with Action plans HEIs adopted
3.2 | Development of supporting documentation to internationalization | UoM finalized supporting documents related to projects, bilateral agreements and degree seeking students and supporting documents related to mobility. UDG and UNIM to finalise their supporting documentation.
3.3 | Design of catalogues for courses offered in English | Catalogues of courses prepared for a number of faculties at UoM

## Slide 4
3.4 | Development of pilot summer school in English with curricula | Summer school programs designed by UoM, including course content and the learning outcomes, application and recruitment procedures, arrangement of housing for the students and development of a social program. UoM to form a Commission for consideration of the proposals, after which the UoM Senate will adopt them and they will be forwarded to AKOKVO for accreditation.
3.6 | Developing criteria for assessing quality of internationalization of Montenegrin HEIs | Criteria for assessing quality of internationalization of Montenegrin HEIs have been developed.

## Slide 5
WP 4 - Integration of Internationalization at Montenegrin HEIs
4.1 | Adoption and implementation of strategic documents | Final versions of internationalization strategies have been adopted. Implementation of internationalization strategies, i.e. their action plans, as well as utilization of the supporting documents for internationalization has started. | 
4.3 | Adoption and implementation of English courses offered at BSc/MSc level | Catalogues of courses offered in English language at BSc/BA and MSc/MA levels are published on the web site as offer for incoming students.
4.4 | Adoption and implementation of pilot summer schools | Summer school curricula with course catalogues, in English, will be presented to UoM’s governing bodies for adoption. After adoption, accreditation process will be performed at National Agency for Quality Assurance of Higher Education. Realisation of summer school will follow accreditation process. During summer school a monitoring visit will be organised, by the delegation which will consist of at least one member from each consortium partner.

## Slide 6
WP 5 - Quality Control and Monitoring
5.2 | Development and implementation of Internal Quality Control and Monitoring Plan | – | Nov. 2021 | All partners | QAB will continue to monitor and assess the quality of project activities and deliverables throughout the project period. The WP leader will prepare two annual QA reports. The second annual report will be prepared at the last month of the project, covering the period from the end of the first year until the end of the project. Satisfaction surveys will be used regularly until the end of the project, elaborated by the WP leader. The data from surveys will be presented in the annual QA reports. The National Erasmus+ Office in Montenegro conducted a monitoring visit of the Erasmus+ project Fostering Internationalization at Montenegrin HEIs through Efficient Strategic Planning – IESP on 14th April 2021

## Slide 7
5.3 | External Quality Control and Evaluation | Nov. 2020 | Dec. 2021 | All partners | External quality control and evaluation of the project planned two times during the project lifetime, by experts engaged through an open call. The first evaluation took place in January 2021, performing quality assessment of the first year of the project. The evaluator prepared first evaluation report, available on the project web site with inputs for improving overall quality of the implementation, and for final report to be submitted to EACEA, and can also serve as background material for project exploitation plan.
5.4 | Impact Analysis | March 2021 | Oct. 2021 | All partners | Detailed impact analysis will be conducted towards the end of the project. The analysis will be used for the development of the Exploitation Roadmap and project final report.

## Slide 8
WP6 - Dissemination and Exploitation of Project Results
6.1 | Development and implementation of dissemination and exploitation plans | – | Nov. 2021 | All partners | Dissemination activities will continued during second project year. Dissemination and exploitation plan to be updated due to the specific situation with COVID-19 pandemic and related restriction measures.
6.2 | Website of the project and social media accounts | – | Nov. 2021 | web network | Website of the project and social media accounts updated regularly.
6.3 | Dissemination products and materials | – | Nov. 2021 |  | Second edition of the Newsletter published on the project web site. First procurement of promotional material completed by the end of December 2020.

## Slide 9
6.4 | Dissemination and exploitation events | IESP project promoted: Erasmus+ project IESP was presented during the event titled „Tell me about your story – what’s on after mobility period? – overcoming the credit recognition challenges after Erasmus+ mobility period“, organized on 25 May at the University of Montenegro within “Europe Month – Erasmus+ Month” At the information day Support for students with disabilities through Erasmus+ projects on Friday, 4th June 2021 At the event “Inclusion and Diversity in Erasmus+ projects at Montenegrin universities” on 15 October 2021 IESP project promoted in the city of Podgorica Within the fifth edition of the Erasmus+ days celebration organized in October 2021, the IESP project was promoted on two advertising boards placed in the city of Podgorica Internationalization Strategy of UoM presented at the EUTOPIA Western Balkans workshop day 2: Internationalisation

## Slide 10
WP7 - Project Management
7.2 | Project meetings | – | Nov. 2021 | In Podgorica or on-line | By the project proposal, in the forthcoming period there should be one PMB meeting, at the end of the project. If necessary, the partners will organize other meetings.
7.3 | Day-to-day management of the project activities | – | Nov. 2021 | All partners | This activity will continue throughout the project period, in accordance with the plan and already established mechanisms and practice, which have shown to be efficient with regard to communication, administration and management. The project partners will submit to the PC semi-annual technical and financial reports.

## Slide 11
7.4 | Periodic and final reports to EACEA | Nov. 2020 | Jan. 2022 | UoM (on behalf of all partners) | The reports will be prepared according to the provisions of the Grant Agreement. The partners will provide all necessary information and reports to the PC in order to compile adequate reports to be sent to EACEA. External evaluation report (to be developed under the activity 5.3) and Impact Analysis (to be developed under the activity 5.4) will contribute to preparation of the final technical report. External audit report (to be developed under the activity 7.5) will contribute to preparation and will be a part of the final financial report.
7.5 | External financial control | Sept. 2021 | Dec. 2021 | All partners | In accordance with the EACEA rules, the PC will engage an external auditor who will conduct a financial audit of the project.