## Slide 1
www.iesp.ucg.ac.me
Fostering Internationalization at Montenegrin HEIs through Efficient Strategic Planning – IESP
Project no. 609675-EPP-1-2019-1-ME-EPPKA2-CBHE-SP
Kick-off Meeting
Podgorica, 15 – 16 January 2020
Prof. Danilo Nikolić, University of Montenegro
This project has been funded with support from the European Commission. This presentation reflects the views only of the author,
and the Commission cannot be held responsible for any use which may be made of the information contained therein.

## Slide 2
AGENDA - WP7: Project management
Presentation of:
Project management principles
Establishing working bodies
  Project Management Board (PMB)
  Quality Assurance (QA) body
  WP Leaders
Partnership Agreements
https://eacea.ec.europa.eu/sites/eacea-site/files/guidelines_for_the_use_of_the_grant_2017_cbhe_v_ii_-_09_january_2018_0.pdf
https://eacea.ec.europa.eu/sites/eacea-site/files/financial_management_2.pdf
Notes: Navedeni prikaz glavnih prioriteta sam kroz razradu preciznije definisao u sedam poglavlja, a zbog vremena ću se osvrnuti samo na one najznačajnije

## Slide 3
Project Contractor / Project Coordinator
Project Management Board PMB
Quality Assurance QA Board
WP1
Leader
WP2
Leader
WP3
Leader
WP4
Leader
WP5
Leader
WP6
Leader
WP7
Leader

## Slide 4
Project Contractor / Project Coordinator
Project Management Board PMB
Quality Assurance QA Board
WP1
Leader
WP2
Leader
WP3
Leader
WP4
Leader
WP5
Leader
WP6
Leader
WP7
Leader
Project Coordinator is responsible for the achievement of the project outcomes, as well as for:
overall project management (technical and operational),
communication and reporting to EACEA,
efficient use of the project grant, etc.

## Slide 5
Project Contractor / Project Coordinator
Project Management Board PMB
Quality Assurance QA Board
WP1
Leader
WP2
Leader
WP3
Leader
WP4
Leader
WP5
Leader
WP6
Leader
WP7
Leader
PMB: decision-making body consisting of one representative (preferably the contact person) from each partner institution.
PMB will meet twice a year (in combination with other project events due to cost efficiency)
to discuss and review the progress of project activities,
to make decisions,
to approve deliverables, and
to agree on any risk contingency measures.

## Slide 6
Project Contractor / Project Coordinator
Project Management Board PMB
Quality Assurance QA Board
WP1
Leader
WP2
Leader
WP3
Leader
WP4
Leader
WP5
Leader
WP6
Leader
WP7
Leader
The QA Board consisting of one representative from each partner institution.
The QA board is a direct support to the PMB in
monitoring and assessing the quality of the project and its results,
in development of Quality and Assurance Plan.

## Slide 7
Project Contractor / Project Coordinator
Project Management Board PMB
Quality Assurance QA Board
WP1
Leader
WP2
Leader
WP3
Leader
WP4
Leader
WP5
Leader
WP6
Leader
WP7
Leader
WP’s Leaders responsible for monitoring of the overall progress of the WP’s and their activities.

## Slide 8: WP 7.1 Establishment of Project management structures
Main Decision Making Body is the PMB.
Project Management Board (PMB) is to be proposed right after the beginning of the project, and officially appointed at the Kick-off meeting.
Each consortium partner will be represented in the PMB, with the coordinator being in the charge of the board.
It will be the main decision-making body of the project, with 2/3 decision-making.
PMB will have responsibility for planning, directing, strategic management, monitoring and control of the project implementation.
Also, PMB will be in charge of the monitoring of implementation of Partnership Agreements that will be signed between coordinator and each consortium partner.

## Slide 9: WP 7.2 Project meetings
During the project lifetime, 3 PMB two-day meetings will be held.
  First meeting will be held during Kick-off meeting (M3) at P1,
  Second meeting at the end of first project year (M12) at P4, and
  Third meeting at the end of the final project year (M24) at P1.
In addition to face-to-face meetings, video conferences and/or skype conferences may be organized, as needed, for decision making purposes.
Also, all WP meetings will be used for the purpose of coordination meetings.
After each meeting, minutes will be prepared and approved via e-mail by the PMB.

## Slide 10: WP 7.3 Day-to-day management of the project
Day-to-Day management will be maintained through communication on the level of consortium, WPs, or even tasks.
The communication will be via e-mail, phone, or other means deemed suitable.
In order to facilitate this process, Project Handbook will be prepared by the Project Coordinator and adopted by the PMB at the beginning of the project.
Also, individual Partnership Agreements will contribute to setting basis and guidelines for smooth and transparent coordination, as they will define roles and responsibilities of coordinator and all partners, reflecting the Grant Agreement and internal set of rules for coordination.

## Slide 11: WP 7.4 Periodic and final reports to EACEA
Following the rules set in the Grant Agreement, Project Coordinator will submit two reports to EACEA during the project implementation – Interim and Final reports.
All project partners will take part in its completion by providing reports for their institutions. Also, they will be in day-to-day communication with the Coordinator until the end of the reporting. The Coordinator may choose to make on-site visits to partners, if deemed necessary for meeting reporting obligations.
As part of the final report, obligatory audit report will also be submitted. Audit will be carried out by an independent external auditor, with experience in auditing internationally funded projects.
The Coordinator will submit the reports to EACEA, and also inform project partners on feedback received.

## Slide 12: WP 7.5 External financial control
P1 will provide external financial audit of the project by the authorized organization in accordance with existing legislation.

## Slide 13
AGENDA - Establishment of Project Management Board and Quality Assurance Body
Notes: Navedeni prikaz glavnih prioriteta sam kroz razradu preciznije definisao u sedam poglavlja, a zbog vremena ću se osvrnuti samo na one najznačajnije

## Slide 14
Project management board PMB
No. | Acronym | Name
1 | UoM | Nataša Kostić
2 | UDG | Milica Vukotić
3 | UNIM | Radislav Jovović
4 | UCA F | Srđan Redžepagić
5 | UL | Katja Cerar
6 | UCA E | Juan Carlos Garcia
7 | MoE | Mubera Kurperjović
8 | MoS-ME | Saša Ivanović
9 | ACQAHE | Tijana Stanković
Project coordinator: prof. dr Danilo Nikolić

## Slide 15
Quality Assurance (QA) body
No. | Acronym | Name
1 | UoM | Vladan Perazić
2 | UDG | Sandra Tinaj
3 | UNIM | Slobodanka Krivokapić
4 | UCA F | Clement Moreau
5 | UL | Tomaž Deželan
6 | UCA E | Rafael Velez Nunez
7 | MoE | Marko Vukašinović
8 | MoS-ME | Lidija Vukčević
9 | ACQAHE | Milica Kavedžić

## Slide 16
WP Leaders
WP No. | WP Leader/Acronym | Name
1 | UCA F | Srđan Redžepagić
2 | UL | Katja Cerar
3 | UoM | Danilo Nikolić
4 | UDG | Bojana Mališić
5 | UCA E | Juan Carlos Garcia Galindo
6 | UNIM | Milica Kovačević
7 | UoM | Prof. dr Nataša Kostić

## Slide 17
AGENDA - Partnership Agreements
Partnership Agreement
Fostering Internationalization at Montenegrin HEIs through Efficient Strategic Planning
IESP
Project reference number:609675-EPP-1-2019-1-ME-EPPKA2-CBHE-SP
2019-1944/001-001
Article 5
Payment arrangements
Taking in account how to spend as soon as possible 70 % of first EACEA instalment
It is important to purchase equipment as soon as possible in order to spend 70 % of the first instalment MNE HEIs
Payment arrangements different for MNE HEIs and for the rest of consortium
Notes: Navedeni prikaz glavnih prioriteta sam kroz razradu preciznije definisao u sedam poglavlja, a zbog vremena ću se osvrnuti samo na one najznačajnije

## Slide 18
Payment(s) in advance ... Example for MNE HEI
The Coordinator will transfer to the respective account of the Beneficiary, in advance of the actual expenditures, 90% of the maximum total amount specified in the estimated Erasmus+ grant contribution identified under Annex 1 of this Agreement, in the following way:
1. First instalment of 60% of the Beneficiary's maximum Erasmus+ grant contribution, deducted for the funds intended for equipment purchase, within 30 days after the signing of the Agreement.
The transfer of the part of Erasmus+ grant contribution for Equipment costs identified under Annex I of this Agreement will be implemented as payment in advance of purchase cost of equipment stipulated in awarded contract ...
2. Second instalment of 25% of the Beneficiary's maximum Erasmus+ grant contribution within 30 days after the Coordinator has received and approved the necessary proofs of expenditures/activities already payed under previous instalment, provided that the Coordinator has received the second pre-financing payment from the Executive Agency. In addition, the Beneficiary will have to meet following conditions: i) purchased all the equipment following the Erasmus+ CBHE rules about equipment purchasing and ii) demonstrated expenditure covering at least 80% of the total amount already transferred, including the amount related to equipment.
3. Third instalment of 5% of the Beneficiary’s maximum Erasmus+ grant contribution, within 30 days after the Coordinator has received and approved necessary proofs (all supporting documents) for the spent funds from the first and second instalments, under above points 1 and 2. In addition, the Beneficiary will have to demonstrate expenditure covering at least 90% of the total amount already transferred in previous instalments.
5.3 Erasmus+ grant amounts received in advance and not used by the Beneficiary will be reimbursed to the Coordinator at the latest 30 days after the end of the project's contractual period.

## Slide 19
Payment(s) in advance Example for rest of consortium
The Coordinator will transfer to the respective account of the Beneficiary, in advance of the actual expenditures, 90% of the maximum total amount specified in the estimated Erasmus+ grant contribution identified under Annex 1 of this Agreement, in the following way:
First instalment of 30% of the Beneficiary's maximum Erasmus+ grant contribution within 30 days after the signing of the Agreement.
Second instalment of 50% of the Beneficiary's maximum Erasmus+ grant contribution within 30 days after the Coordinator has received and approved the necessary proofs (all supporting documents) of expenditures/activities already payed under previous instalment, provided that the Coordinator has received the second pre-financing payment from the Executive Agency. In addition, the Beneficiary will have to demonstrate expenditure covering at least 80% of the total amount already transferred in pervious instalment.
Third instalment of 10% of the Beneficiary’s maximum Erasmus+ grant contribution, within 30 days after the Coordinator has received and approved necessary proofs (all supporting documents) for the spent funds from the first and second instalments, under above points 1 and 2. In addition, the Beneficiary will have to demonstrate expenditure covering at least 90% of the total amount already transferred in previous instalments.
5.3 Erasmus+ grant amounts received in advance and not used by the Beneficiary will be reimbursed to the Coordinator at the latest 30 days after the end of the project's contractual period.

## Slide 20
Final payment
5.4 If applicable, final instalment of the grant to be transferred to the Beneficiary by the Coordinator (up to the remaining 10% of the Beneficiary’s maximum Erasmus+ grant contribution) will be defined once the total Erasmus+ grant has been confirmed by the Executive Agency after the end of the project and approval of the Coordinator’s final financial statement. This instalment will be transferred to the Beneficiary within 30 days after the receipt of final balance payment from the Executive Agency.
5.5 In the event there is a difference between the amount of the Erasmus+ grant contribution actually used by the partnership and the amount of expenditure declared eligible by the Executive Agency at the end of the project, if responsible for the expenditure declared ineligible, the Beneficiary will reimburse the corresponding amount to the Coordinator within 20 days from the date of the receiving the notice from the Coordinator.
5.6 The costs of dispatching funds to the beneficiary will be paid by the Coordinator and the cost of receiving funds (which may be charged by the receiving institution’s bank) will be paid by the receiving institution.

## Slide 21
Thank you for attention