## Slide 1
http://www.iesp.ucg.ac.me/
Project no. 609675-EPP-1-2019-1-ME-EPPKA2-CBHE-SP
Fostering Internationalization at Montenegrin HEIs through Efficient Strategic Planning – IESP
Project Management Board meeting
13 November 2020

## Slide 2
Fostering Internationalization at Montenegrin HEIs through Efficient Strategic Planning – IESP
Project no. 609675-EPP-1-2019-1-ME-EPPKA2-CBHE-SP
 | YEAR 1 |  |  |  |  |  |  |  |  |  |  |  | YEAR 2 |  |  |  |  |  |  |  |  |  |  | 
WPs | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
WP1 (PREPARATION) | Nov. 2019 |  |  |  |  |  | June 2020 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WP2 (DEVELOPMENT) |  |  |  | Mar. 2020 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Nov. 2021
WP3 (DEVELOPMENT) |  |  |  |  |  |  |  | July 2020 |  |  |  |  |  |  |  |  |  | May 2021 |  |  |  |  |  | 
WP4 (DEVELOPMENT) |  |  |  |  |  |  |  |  |  |  | Oct. 2020 |  |  |  |  |  |  |  |  |  |  |  |  | Nov. 2021
WP5 (QUALITY PLAN) |  |  | Feb. 2020 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Nov. 2021
WP6 (DISS & EXPL) | Nov. 2019 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Nov. 2021
WP7 (MANAGEMENT) | Nov. 2019 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Nov. 2021

## Slide 3
Fostering Internationalization at Montenegrin HEIs through Efficient Strategic Planning – IESP
Project no. 609675-EPP-1-2019-1-ME-EPPKA2-CBHE-SP
Development of tools for enhanced internationalization WP 3 | Activities |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | Due date
 | WP/ DEV | Title |  |  |  |  |  |  |  |  |  |  |  |  | 
University of Montenegro | DEV 3.1 | Development of internationalization strategies and action plans |  |  |  |  |  |  |  | July 2020 |  |  | Oct. 2020 |  | 15 Oct. 2020
 | DEV 3.2 | Development of supporting documentation to internationalization |  |  |  |  |  |  |  | July 2020 |  |  | Oct. 2020 |  | 15 Oct. 2020
 | DEV 3.3 | Design of catalogues for courses offered in English |  |  |  |  |  |  |  |  |  |  | Oct 2020 |  | 15 Dec. 2020
 | DEV 3.4 | Development of pilot summer school in English with curricula |  |  |  |  |  |  |  | July 2020 |  |  |  |  | 15 Dec. 2020
 | DEV 3.5 | Development of teaching matarials in English |  |  |  |  |  |  |  |  |  |  |  |  | 15 May 2021
 | DEV 3.6 | Developing criteria for assessing the quality of internationalization of Montenegrin HEIs |  |  |  |  |  |  |  | July 2020 |  |  |  |  | 14 Nov. 2020

## Slide 4
Fostering Internationalization at Montenegrin HEIs through Efficient Strategic Planning – IESP
Project no. 609675-EPP-1-2019-1-ME-EPPKA2-CBHE-SP
Manage- ment WP 7 | Activities |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
 | WP/ DEV | Title |  |  |  |  |  |  |  |  |  |  |  | 
University of Montenegro | MNGT 7.1 | Establishment of project management structures | Nov. 2019 |  | Jan. 2020 |  |  |  |  |  |  |  |  | 
 | MNGT 7.2 | Project meetings |  |  | Jan. 2020 |  |  |  |  |  |  |  |  | Nov. 2020
 | MNGT 7.3 | Day-to-day management of project activities | Nov. 2019 |  |  |  |  |  |  |  |  |  |  | Nov. 2020
 | MNGT 7.4 | Periodic and final reports to EACEA |  |  |  |  |  |  |  |  |  |  |  | Nov. 2020
 | MNGT 7.5 | External financial control |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 5
Thank you for your attention
http://www.iesp.ucg.ac.me/
Project no. 609675-EPP-1-2019-1-ME-EPPKA2-CBHE-SP